## Sheet1
Jemillee Prade: Blue Sandy MacAskill: Green FelipeMafra Dos Santos: Yellow All: Red | Week 3 Inception (20) | Due Week 4 | Due Week 5 | Due Week 6 | Due Week 7 | Due Week 8 | Due Week 9 | Due Week 10 | Due Week 11 | Due Week 12 | Due Week 13 | Due Week 14 | Due Week 15
Inception
Client Letter |  | 2020-02-08
Team Charter (Letter to Client, IP) |  | 2020-02-08
Project Charter (Stakeholders Decription) |  | 2020-02-08
IP Contract Between Client and Team Members |  | 2020-02-08
IP Contract Between Team Members |  | 2020-02-08
Project Plan |  | 2020-02-05
Web Search and Rationale Report |  | 2020-02-08
Team Status Report |  | 2020-02-08
Client Sign-off document |  | 2020-02-08
Project Summation Slides |  | 2020-02-08
Development | Analysis
Database Coding | Database Design |  | 2020-02-14
Web shell with database interaction | Database Design |  |  | 2020-02-21
User accounts added | Database Design | [5 empty] | 2020-03-13
Web page layouts implemented |  |  |  |  | 2020-02-28 |  |  | 2020-03-20 |  | 2020-04-03
Import Bulk Data | [7 empty] | 2020-03-20
Report Generations | [8 empty] | 2020-03-27
Analysis
Agile Iteration Plan |  |  | 2020-02-14
Use Case Diagrams |  |  |  | 2020-02-21
Use Case Descriptions (Limit 5 significant) |  |  | 2x 14-Feb | 2x 21-Feb | 1x 28-Feb
Analysis level (Domain) Class Diagram |  |  |  | 2020-02-17
System Sequence Diagrams (Limit 3 significant) |  |  |  | 1x 21-Feb | 1x 28-Feb | 1x 6-Mar
Statechart Diagram(s) for complex classes (Limit 3 significant)
Client Sign-off Document |  |  | 2020-02-14 | 2020-02-21 | 2020-02-28 |  | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03
Team Status Report (Weekly) |  |  | 2020-02-14 | 2020-02-21 | 2020-02-28 |  | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03
Agile Backlog |  |  |  |  | 2020-02-28
Agile Release Summary |  |  |  |  | 2020-02-28
Design
Design Class Diagram |  |  |  | 2020-02-21
Design level Sequence Diagrams (Limit 3 Significant) | [6 empty] | 1x 13-Mar | 1x 20-Mar | 1x 27-Mar
Navigation Diagram(s) | [6 empty] | 2020-03-13
User Interface Prototype |  |  |  | 2020-02-21
Entity Relationship Diagram (ERD) | [7 empty] | 2020-03-20
Data Dictionary with field level definitions or Glossary | [10 empty] | 2020-04-10
Construction
Agile Iteration Summary
Unit Tests Plan and Results | [6 empty] | 2020-03-13
Working Code Demonstration |  |  | 2020-02-14 |  | 2020-02-28 |  | 2020-03-13 | 2020-03-20 |  | 2020-04-03 | 2020-04-10 | 2020-04-17
Transition
User and System test plan(s) and results | [10 empty] | 2020-04-10
Help system (User doc) and (if created) tutorials | [10 empty] | 2020-04-10
Project ID Sheet & Deployment Guide | [10 empty] | 2020-04-10
Source Code & Deployment to Client | [10 empty] | 2020-04-10
Faculty Advisor Project Submission (check the Project Submission Specification) | [10 empty] | 2020-04-10
Client Project Submission (check the Project Submission Specification) | [10 empty] | 2020-04-10
Agile Backlog | [9 empty] | 2020-04-03
Agile Release Summary | [9 empty] | 2020-04-03
Demo and Judging
Attending Demo Day | [12 empty] | 2020-04-22
Application Brochure | [12 empty] | 2020-04-22
Business Cards | [12 empty] | 2020-04-22
Resumes | [12 empty] | 2020-04-22
Showroom Slides | [12 empty] | 2020-04-22
Booth Display | [12 empty] | 2020-04-22