## Sheet1
Conestoga College
Team: | Sandy MacAskill, Felipe Mafra, Jemillee Prado
Agile Product Feature List - Backlog Template
# | Description
| High Priority | PD est.
Inception
1.3 | Project Charter | 1
1.4 | IP Contract | 1
1.5 | Project Plan | 1
1.7 | Project Summation Slides | 1
Iteration 1
2.1 | Database Design | 2
2.2 | Database Coded | 1
2.3 | Database Review | 1
2.4 | Code Add User Web Page | 6
4.4 | User Interface Prototype | 2
5.3 | Database Demonstration | 0.5
5.4 | Add User Page code demonstration | 0.5
Iteration 2
2.5 | Code for Additional Web Pages | 8
2.5.1 | Code Product CRUD Page | 2
2.5.2 | Code Store CRUD Page | 0.5
2.5.3 | Code Supplier CRUD Page | 0.5
2.5.4 | Code City CRUD Page | 0.5
2.5.5 | Code Category CRUD Page | 1
2.5.6 | Code Shipping Company CRUD Page | 0.5
4.2 | Design level Sequence Diagrams | 2
4.3 | Navigation Diagram(s) | 2
4.5 | Entity Relationship Diagram (ERD) | 2
5.5 | Add User Page UI demonstration | 0.5
5.6 | Store/Product page code demonstration | 0.5
5.7 | UI for additonal pages demonstration | 0.5
Iteration 3
2.7 | Code Security Checks | 8
2.9 | Report Generation | 8
5.9 | Report Demonstration | 2
6.1 | Validation testing | 6
6.2 | Security testing | 6
Transition
5.2 | Unit Tests Plan and Results - Admin | 3
| Unit Tests Plan and Results - User | 3
7.1 | User and System test plan(s) and results | 1
7.2 | Help system and tutorials | 1
7.3 | Project ID Sheet & Deployment Guide | 2
7.4 | Source Code & Deployment to Client | 1
7.5 | Faculty Advisor Project Submission | 1
7.6 | Client Project Submission | 1
Medium Priority
1.1 | Client Letter
1.6 | Web Search and Rationale Report
2.4.1 | UI for Add User Web Page
3.1 | Agile Iteration Plan
3.2 | Use Case Diagrams
3.3 | Use Case Descriptions x 2
3.4 | Use Case Descriptions x 2
3.5 | Use Case Descriptions x 1
3.6 | Statechart Diagrams
3.7 | Agile Backlog
3.8 | Agile Release Summary
4.1 | Design Class Diagram
5.1 | Agile Iteration Summary
2.6 | UI for Additional Web Pages
7.7 | Agile Backlog
7.8 | Agile Release Summary
Low Priority
8.1 | Attending Demo Day
8.2 | Resumes
8.3 | Booth Display