## Sheet1
Conestoga College
Team: | Sandy MacAskill, Felipe Mafra, Jemillee Prado
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition | Presentation
|  | Due: Feb-07 | Due: Mar-1 | Due: Mar-22 | Due: Apr-12 | Due: Apr-19 | Due: Apr-23
# | Feature / Requirement
1 | INCEPTION
1.1 | Client Letter | 1
1.2 | Team Charter | 1
1.3 | Project Charter | 1
1.4 | IP Contract | 1
1.5 | Project Plan | 1
1.6 | Web Search and Rationale Report | 3
1.7 | Project Summation Slides | 1
2 | DEVELOPMENT
2.1 | Database Design |  | 2
2.2 | Database Coded |  | 1
2.3 | Database Review |  | 1
2.4 | Code Add User Web Page |  | 6
2.4.1 | UI for Add User Web Page |  | 4
2.5 | Code for Additional Web Pages |  |  | 8
2.5.1 | Code Product CRUD Page |  |  | 2
2.5.2 | Code Store CRUD Page |  |  | 0.5
2.5.3 | Code Supplier CRUD Page |  |  | 0.5
2.5.4 | Code City CRUD Page |  |  | 0.5
2.5.5 | Code Category CRUD Page |  |  | 1
2.5.6 | Code Shipping Company CRUD Page |  |  | 0.5
2.6 | UI for Additional Web Pages |  |  | 9
2.7 | Code Security Checks |  |  |  | 8
2.8 | Import Bulk Data
2.9 | Report Generation |  |  |  | 8
3 | ANALYSIS
3.1 | Agile Iteration Plan |  | 0.5
3.2 | Use Case Diagrams |  | 5
3.3 | Use Case Descriptions x 2 |  | 0.5
3.4 | Use Case Descriptions x 2 |  | 0.5
3.5 | Use Case Descriptions x 1 |  | 0.5
3.6 | Statechart Diagrams |  | 5
3.7 | Agile Backlog |  | 1
3.8 | Agile Release Summary |  | 1
4 | DESIGN
4.1 | Design Class Diagram |  | 2
4.2 | Design level Sequence Diagrams |  |  | 2
4.3 | Navigation Diagram(s) |  |  | 2
4.4 | User Interface Prototype |  | 2
4.5 | Entity Relationship Diagram (ERD) |  |  | 2
5 | CONSTRUCTION
5.1 | Agile Iteration Summary |  | 1
5.2 | Unit Tests Plan and Results - Admin |  |  |  |  | 3
| Unit Tests Plan and Results - User |  |  |  |  | 3
5.3 | Database Demonstration |  | 0.5
5.4 | Add User Page code demonstration |  | 0.5
5.5 | Add User Page UI demonstration |  |  | 0.5
5.6 | Store/Product page code demonstration |  |  | 0.5
5.7 | UI for additonal pages demonstration |  |  | 0.5
5.8 | Bulk Data Demonstration
5.9 | Report demonstration | 0.5 | 0.5 | 0.5 | 0.5
6 | QUALITY ASSURANCE
6.1 | Validation testing |  | 2 | 2 | 2
6.2 | Security testing |  | 2 | 2 | 2
7 | TRANSITION
7.1 | User and System test plan(s) and results |  |  |  |  | 1
7.2 | Help system and tutorials |  |  |  |  | 1
7.3 | Project ID Sheet & Deployment Guide |  |  |  |  | 2
7.4 | Source Code & Deployment to Client |  |  |  |  | 1
7.5 | Faculty Advisor Project Submission |  |  |  |  | 1
7.6 | Client Project Submission |  |  |  |  | 1
7.7 | Agile Backlog |  |  |  | 1
7.8 | Agile Release Summary |  |  |  | 1
8 | DEMO AND JUDGING
8.1 | Attending Demo Day |  |  |  |  | 0
8.2 | Resumes |  |  |  |  | 0
8.3 | Booth Display |  |  |  |  | 0
| Work Effort in Person Days (PD) | 9.5 | 38.5 | 34 | 22.5 | 13 |  | 117.5
* 1PD = 2H